## Project Information
[5 empty] | UTC | Enhancing Durability and Service Life of Infrastructure | Asphalt Concrete Materials | Proposal
Project No. | 19CTAM01 |  |  |  | External | Preserving Existing Transportation Systems | Portland Cement Concrete Materials | Technical | Amount Should be Expensed | #REF!
Project Title | Modeling Sulfate Attack in Modern Concrete for Building Sustainable and Resilient Infrastructure |  |  |  | - | Preserving the Environment | Geotechnical | Implementation | Amount Expensed | 19000
Lead Institution | Texas A&M University |  |  |  |  | Addressing other Region 6 Transportation Needs | Intelligent Transportation Systems | Completed | % Over/Under | #REF!
Collaborative Institution #1 | Louisiana State University | [5 empty] | Pavements
Collaborative Institution #2 | University of Texas at Arlington | [5 empty] | Policy Planning
Collaborative Institution #3 | - | [5 empty] | Safety
Collaborative Institution #4 | - | [5 empty] | Structural
Funds Requested | 45000 | Funds Matching | 45000
Project Start Date | 2019-08-15 | Project End Date | 2021-02-15
Funds Expensed | 19000 | Cost | 5.556%
|  | Schedule | 12.5% | 14.75%
ATTRI | Concept | Applications
Connected Automation | SOW | Concepts & Analysis
Freight Operations | PR | Enabling Technologies
Operations Research | Awarded
Tools Development | Completed

## Progress
Reporting Period | 3
Task | Description |  | Projected Schedule (%) | R1 Progress | R2 Progress | R3 Progress | R4 Progress | R5 Progress | Proposal Start Date | Proposal Due Date | Expected Due Date | Date Delivered | End of Reporting Period: | 2020-05-14 18:00 |  |  | To be reported
1-1 | Identification of Bagasse Ash Microstructure |  | 0 | 25% | 100% |  |  |  | 2019-08-15 | 2020-04-15 | - | 2020-04-15 | 244 | 244 | 244 | 0 | 0
1-2 | Opimization of Production Process to Maximize Pozzolanic Activity |  | 25 | 5% | 55% | 100% |  |  | 2019-08-15 | 2020-04-15 | 2020-06-15 | 2020-06-15 | 244 | 244 | 244 | 61 | 25
1-3 | Experimental Evaluation of Mechanical and Phsical Properties of Concrete with Bagasse Ash |  | 14.7541 |  |  | 55% |  |  | 2019-10-15 | 2020-08-15 | - | - | 305 | 212.75 | 167.75 | 45 | 14.7541
2-1 | Pilot Test for Pavement Road Repair |  | - | [5 empty] | 2020-08-15 | 2020-12-15 | - | - | 122 | 0 | 0 | 0 | -
2-2 | Technology Transfer Activities |  | - | [5 empty] | 2020-08-15 | 2021-02-15 | - | - | 184 | 0 | 0 | 0 | -
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
|  |  | - | [8 empty] | - | - | 0 | #VALUE! | #VALUE! | #VALUE!
G
Task(s) | Reporting Period | If tasks are behind schedule, please indicate the reason(s) why and how they can be addressed. Please feel free to make other schedule-related notes below. | [10 empty] | Y
1-2 | 2 | Materials testing system malfunctioned which has caused delay in testing. Expect to complete testin in R3. | [10 empty] | R
1-3 | 3 | Previous delay has delayed the start of this task. Expect to complete task on time. | [10 empty] | -

## Products
Reporting Period | Product | Status | Please fully describe product (e.g., give citation for publication, list website URL, identify new or revised courses, etc.).
1 | Technology/Technique | Completed | Developed a smart phone application that allows drivers to collect vibration, GPS, and speed information for automated road damage detection and reporting.
2 | Publication | In-Progress | Ashan, M. and Z. Hossain (2019). Effect of particle size of rice husk ash (RHA) in mitigating alkali silica reaction (ASR) in concrete pavement. In review, International Journal of Pavement Research and Techology.
3 | Conference Paper | Completed | Corning-Padilla, A. and G. Rowangould, "Sustainable and equitable financing for pedestrian infrastructure maintenance". Transportation Research Board Annual Meeting, January 2020, Washington, D.C.
3 | Website | Completed | Developed website to further disseminate information and provide regular, public updates: <https://melsatron.com>
3 | New or Revised Course | Completed | An educational module on advanced asphalt testing methods/analyses was added to Louisiana Tech courses "CVEN427: Design of Highway Pavements" and "CVEN517: Advanced Civil Engineering Materials".
3 | Educational Module | Completed | An educational module was developed on the application of rice hull ash in FFC mixtures and presented at a "lunch and learn" event.
3 | Seminar/Workshop | Completed | Moreu, F. and H. Noh. "Quantifying human-infrastructure interfaces for decisions: Theory, applications, and hands-on experiments using data." January 27, 2019, Orlando, FL.
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| - | -
| Conference Paper |  | -
| Educational Module |  | Completed
| New or Revised Course |  | In-Progress
Patent
Publication
Seminar/Workshop
Technology/Technique
Webinar
Website
Other
-

## Expenditures
Total Requested Funds | 30000 |  | Reporting Period | Total Funds Expensed | % Funds Expensed | Cost Indicator (%)
Total Funds Expensed | 19000 |  | 1 | 8500 | 28.33% | 41.67%
% Funds Expensed | 63.33% |  | 2 | 3000 | 10% | -50%
Cost Indicator (%) | 0.055556 |  | 3 | 7500 | 25% | 25%
|  |  | 4 | 0 | 0% | -
|  |  | 5 | 0 | 0% | -
Leading Institution |  |  | Texas A&M University
Requested (UTC) funds expensed per reporting period
|  |  | R1 | R2 | R3 | R4 | R5
|  |  | 7500 | 1000 | 1500
Please comment on the current budget status, and whether the current expenses have been as anticipated. |  | R1 | High expenses due to the purchase of testing material and device.
|  | R2 | Expenses as expected.
|  | R3 | Expenses as expected.
R4
R5
Collaborative Institution #1 |  |  | Louisiana State University
Requested (UTC) funds expensed per reporting period
|  |  | R1 | R2 | R3 | R4 | R5
|  |  | 1000 | 2000 | 5000
Please comment on the current budget status, and whether the current expenses have been as anticipated. |  | R1 | Expenses as expected.
|  | R2 | Expenses as expected.
|  | R3 | Expenses as expected; completed majority of LSU contribution.
R4
R5
Collaborative Institution #2 |  |  | University of Texas at Arlington
Requested (UTC) funds expensed per reporting period
|  |  | R1 | R2 | R3 | R4 | R5
1000
Please comment on the current budget status, and whether the current expenses have been as anticipated. |  | R1 | No expenses; UTA's contribution doesn't begin until R3.
|  | R2 | No expenses; UTA's contribution doesn't begin until R3.
|  | R3 | Expenses as expected.
R4
R5
Collaborative Institution #3 |  |  | -
Requested (UTC) funds expensed per reporting period
|  |  | R1 | R2 | R3 | R4 | R5
Please comment on the current budget status, and whether the current expenses have been as anticipated |  | R1
R2
R3
R4
R5
Collaborative Institution #4 |  |  | -
Requested (UTC) funds expensed per reporting period
|  |  | R1 | R2 | R3 | R4 | R5
Please comment on the current budget status, and whether the current expenses have been as anticipated. |  | R1
R2
R3
R4
R5

## UTC Metrics
Total | Note: Report as to-date metrics (not those solely achieved during the reporting period).
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published | 0 | 1 | 0 | 0 | 0
| Number of Presentations Given | 0 | 0 | 1 | 0 | 0
| Number of Conference Papers Published | 0 | 1 | 0 | 0 | 0
| Number of Students Participating in the Reseach Project | 2 | 10 | 11 | 0 | 0
| Undergraduate Students | 1 | 5 | 8 | 0 | 0
| Graduate Students | 1 | 5 | 3 | 0 | 0
| Number of Students Supported in the Research Project | 2 | 3 | 9 | 0 | 0
| Undergraduate Students | 0 | 0 | 5 | 0 | 0
| Master Students | 1 | 2 | 3 | 0 | 0
| Doctoral Students | 1 | 1 | 1 | 0 | 0
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups | 0 | 1 | 2 | 0 | 0
| Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups | 0 | 0 | 0 | 0 | 0
| Total Budgeted Costs for Women & Minorities | 0 | 5000 | 10000 | 0 | 0
Education | Number of New or Revised Courses Delivered | 0 | 0 | 1 | 0 | 0
| Number of Students Attending the Offered Courses | 0 | 0 | 25 | 0 | 0
| Number of New Transportation-Related Educational Modules Delivered | 0 | 0 | 1 | 0 | 0
| Number of Webinars Presented | 0 | 0 | 1 | 0 | 0
| Estimated Number Attending Presented Webinars | 0 | 0 | 25 | 0 | 0
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 4 | 6 | 0 | 0
| Undegraduate Courses | 0 | 3 | 4 | 0 | 0
| Graduate Students | 0 | 1 | 2 | 0 | 0
| Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students | 4 | 0 | 0 | 0 | 0
| Number of Students Attending Sponsored or Invovled STEM Events | 125 | 0 | 0 | 0 | 0
Workforce Development | Number of Seminars/Workshops Presented | 0 | 0 | 1 | 0 | 0
| Estimated Number Attending Presented Seminars/Workshops | 0 | 0 | 125 | 0 | 0
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 2 | 0 | 0
| Undegraduate Degrees | 0 | 0 | 1 | 0 | 0
| Masters Degrees | 0 | 0 | 1 | 0 | 0
| Doctoral Degrees | 0 | 0 | 0 | 0 | 0
| Number of Graduated, Supported Students Entering the Transportation Field | 0 | 0 | 1 | 0 | 0
| Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students | 1 | 0 | 1 | 0 | 0
Leading Institution | Texas A&M University
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published |  | 1
| Number of Presentations Given |  |  | 1
| Number of Conference Papers Published |  | 1
| Number of Students Participating in the Reseach Project | 2 | 9 | 4 | 0 | 0
| Undergraduate Students | 1 | 5 | 3
| Graduate Students | 1 | 4 | 1
| Number of Students Supported in the Research Project | 2 | 2 | 2 | 0 | 0
Undergraduate Students
| Master Students | 1 | 1 | 1
| Doctoral Students | 1 | 1 | 1
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups |  | 1 | 1
Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups
| Total Budgeted Costs for Women & Minorities |  | 5000 | 7500
Education | Number of New or Revised Courses Delivered |  |  | 1
| Number of Students Attending the Offered Courses |  |  | 25
| Number of New Transportation-Related Educational Modules Delivered |  |  | 1
Number of Webinars Presented
Estimated Number Attending Presented Webinars
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 4 | 4 | 0 | 0
| Undegraduate Courses |  | 3 | 3
| Graduate Students |  | 1 | 1
| Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students | 4
| Number of Students Attending Sponsored or Invovled STEM Events | 125
Workforce Development | Number of Seminars/Workshops Presented
Estimated Number Attending Presented Seminars/Workshops
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 1 | 0 | 0
Undegraduate Degrees
| Masters Degrees |  |  | 1
Doctoral Degrees
| Number of Graduated, Supported Students Entering the Transportation Field |  |  | 1
| Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students | 1
Collaborative Institution #1 | Louisiana State University
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published
Number of Presentations Given
Number of Conference Papers Published
| Number of Students Participating in the Reseach Project | 0 | 1 | 1 | 0 | 0
Undergraduate Students
| Graduate Students |  | 1 | 1
| Number of Students Supported in the Research Project | 0 | 1 | 1 | 0 | 0
Undergraduate Students
| Master Students |  | 1 | 1
Doctoral Students
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups
Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups
Total Budgeted Costs for Women & Minorities
Education | Number of New or Revised Courses Delivered
Number of Students Attending the Offered Courses
Number of New Transportation-Related Educational Modules Delivered
| Number of Webinars Presented |  |  | 1
| Estimated Number Attending Presented Webinars |  |  | 25
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 0 | 0 | 0 | 0
Undegraduate Courses
Graduate Students
Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students
Number of Students Attending Sponsored or Invovled STEM Events
Workforce Development | Number of Seminars/Workshops Presented |  |  | 1
| Estimated Number Attending Presented Seminars/Workshops |  |  | 125
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 0 | 0 | 0
Undegraduate Degrees
Masters Degrees
Doctoral Degrees
Number of Graduated, Supported Students Entering the Transportation Field
| Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students |  |  | 1
Collaborative Institution #2 | University of Texas at Arlington
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published
Number of Presentations Given
Number of Conference Papers Published
| Number of Students Participating in the Reseach Project | 0 | 0 | 6 | 0 | 0
| Undergraduate Students |  |  | 5
| Graduate Students |  |  | 1
| Number of Students Supported in the Research Project | 0 | 0 | 6 | 0 | 0
| Undergraduate Students |  |  | 5
| Master Students |  |  | 1
Doctoral Students
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups |  |  | 1
Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups
| Total Budgeted Costs for Women & Minorities |  |  | 2500
Education | Number of New or Revised Courses Delivered
Number of Students Attending the Offered Courses
Number of New Transportation-Related Educational Modules Delivered
Number of Webinars Presented
Estimated Number Attending Presented Webinars
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 0 | 2 | 0 | 0
| Undegraduate Courses |  |  | 1
| Graduate Students |  |  | 1
Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students
Number of Students Attending Sponsored or Invovled STEM Events
Workforce Development | Number of Seminars/Workshops Presented
Estimated Number Attending Presented Seminars/Workshops
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 1 | 0 | 0
| Undegraduate Degrees |  |  | 1
Masters Degrees
Doctoral Degrees
Number of Graduated, Supported Students Entering the Transportation Field
Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students
Collaborative Institution #3 | -
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published
Number of Presentations Given
Number of Conference Papers Published
| Number of Students Participating in the Reseach Project | 0 | 0 | 0 | 0 | 0
Undergraduate Students
Graduate Students
| Number of Students Supported in the Research Project | 0 | 0 | 0 | 0 | 0
Undergraduate Students
Master Students
Doctoral Students
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups
Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups
Total Budgeted Costs for Women & Minorities
Education | Number of New or Revised Courses Delivered
Number of Students Attending the Offered Courses
Number of New Transportation-Related Educational Modules Delivered
Number of Webinars Presented
Estimated Number Attending Presented Webinars
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 0 | 0 | 0 | 0
Undegraduate Courses
Graduate Students
Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students
Number of Students Attending Sponsored or Invovled STEM Events
Workforce Development | Number of Seminars/Workshops Presented
Estimated Number Attending Presented Seminars/Workshops
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 0 | 0 | 0
Undegraduate Degrees
Masters Degrees
Doctoral Degrees
Number of Graduated, Supported Students Entering the Transportation Field
Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students
Collaborative Institution #4 | -
Category | Description of Indicator | R1 Metrics | R2 Metrics | R3 Metrics | R4 Metrics | R5 Metrics
Research | Number of Peer-Reviewed Publications Published
Number of Presentations Given
Number of Conference Papers Published
| Number of Students Participating in the Reseach Project | 0 | 0 | 0 | 0 | 0
Undergraduate Students
Graduate Students
| Number of Students Supported in the Research Project | 0 | 0 | 0 | 0 | 0
Undergraduate Students
Master Students
Doctoral Students
Diversity | Number of Research Opportunites for Graduate Students from Underrepresentative Groups
Number of Research Opportunites for Undergraduate Students from Underrepresentative Groups
Total Budgeted Costs for Women & Minorities
Education | Number of New or Revised Courses Delivered
Number of Students Attending the Offered Courses
Number of New Transportation-Related Educational Modules Delivered
Number of Webinars Presented
Estimated Number Attending Presented Webinars
| Number of Transportation-Related Courses Taught by PIs and/or TAs Associated with Project | 0 | 0 | 0 | 0 | 0
Undegraduate Courses
Graduate Students
Number of STEM Events Sponsored by the Project or Otherwise Participated in by PIs or Supported students
Number of Students Attending Sponsored or Invovled STEM Events
Workforce Development | Number of Seminars/Workshops Presented
Estimated Number Attending Presented Seminars/Workshops
| Number of Supported Students Who Received Degrees during Reporting Period | 0 | 0 | 0 | 0 | 0
Undegraduate Degrees
Masters Degrees
Doctoral Degrees
Number of Graduated, Supported Students Entering the Transportation Field
Number of Professional Society-Related Events Sponsored by the Project or Otherwise Participated in by PIs or Supported Students

## Instructions
Reporting Periods
• Progress should be reported according to the defined periods below. • These periods are referenced throughout this Workbook as R1 (Reporting Period 1), R2 (Reporting Period 2), and so on.
| Reporting Period | Date Period Starts | Date Period Ends
| 1 | 2019-08-15 | 2019-12-16
| 2 | 2019-12-17 | 2020-04-15
| 3 | 2020-04-16 | 2020-08-17
| 4 | 2020-08-18 | 2020-11-16
| 5 | 2020-11-17 | 2021-02-15
Color Legend
| White | Fields that are updated on a non-recurring basis (typically at the project start).
| Blue | Fields that are updated on a quarterly basis (by the PI).
| Gray | Locked fields that cannot be edited (contain internal logic to calculate performance indicators).
| Tan | Table and section headings.
Clarifications and Reminders
| Excel Tab | Clarifications and Reminders
| "Progress" | Please indicate the percent completion of each task. If a task is complete, please input "100" and update the corresponding "Date Delivered" column with an estimated date of when the task was completed.
| "Products" | Please indicate the product type and status for each inputted product. "In-Progress" products would include submissions to conferences, journal submissions, an application for a patent, etc. Corresponding "Completed" products would include conference presentations given, articles published, patents received, etc.
| "Expenditures" | Expenditures only include requested (UTC) funds. Please input funds on a per reporting period basis and not a running total.
| "UTC Metrics" | Please input metrics on a per reporting period basis and not a running total. "Minority" is defined as an underrepresented group in the field of STEM: African Americans, American Indians/Alaska Natives, and Latinos. This also includes females.
Please be consistent in inputting "Products" and "UTC Metrics". For example, a conference presentation listed in the "Products" section should also be reported under the corresponding field in the "UTC Metrics" field.
Excel Tips
• To easily add a bullet in Excel, use the keyboard shortcut of "ALT+7". • To easily add/skip to the next line in Excel, use the keyboard shortcut of "ALT+Spacebar".
Contact
• If you have any issues in filling out the tracker, please contact Mr. Christopher Melson at transet@lsu.edu or (225) 578-3805. • For more information, including access to the a template and an example, please visit Tran-SET's website: http://transet.lsu.edu/pi-toolbox/.